## Sheet1
| Work Task | Sections Responsible | Resources Required | Goals/Measurement | Date Due | Relevant Strategic Plan Element
Organizing and Providing Access to Material
1 | Significantly expand metadata activity among Center staff. For example, begin cataloging maps to be digitized, complete AIDS Posters, Arkatov, Cashin, Eighth & Wall projects; guide LA Daily News, Movie Stills and other projects. | All | existing staff; ability to significantly expand shelf ready processing and to depend on cat-on-receipt | Measurement: Digital projects will regularly be taking place concurrently. It will be common for staff to spend at least one day a week on metadata activity. Stats will be developed to track digital project activity; baselines will be established. | 2011-07-01 | Goal C: Make Specialized Collections Accessible
2 | Complete the work of the Mellon Hidden Collections grant project | Project staff; Train & Doc | Grant-funded staff and existing staff (Library cost-share); possible back-up support from Metadata TF | Measurement: At least 55,000 titles will be cataloged/processed. | 2011-06-30 | Goal C: Make Specialized Collections Accessible
3 | Prepare priority batches of YRL stacks materials for Google digitization by completing non-roman recon | Train & Doc; Metadata TF; Monocats | existing staff & students; possibly some limited appt funding [being assessed] | Measurement: Throughout the year selected priority classification ranges are completed the material is folded into shipments to Google. | 2011-07-01 | Goal C: Make Specialized Collections Accessible
4 | Eliminate backlogs and consolidate leftovers. Develop and implement new strategies, including experimenting with "floating" limited appointments or students with specific language skills who could meet needs in various Library areas | Eliminating Backlogs & Improving Bibliographic Access Group | existing staff | Measurement: Some backlogs will be cited as being eliminated/reduced. Minimal level cataloging will be caught up, except where language skills are lacking. An e-serials backlog of 500 titles will be caught up. Maps will be cataloged in support of digitization. | 2011-07-01 | Goal C: Make Specialized Collections Accessible
5 | Increase access to Non-Roman/Specialized Material/Hidden Collections | All; Print Acq; assistance from CRIS | existing staff | Measurement: Provisional access to newly-received non-roman material is brought about through collaboration with Print Acq on a pilot for vernacular-only data input for at least one language. Collection-level records are employed for appropriate materials, for which we lack the necessary language expertise. Minasian grant metadata for Arabic and Persian materials are mapped to MARC records and loaded to WorldCat. | 2011-07-01 | Goal C: Make Specialized Collections Accessible
6 | Catalog and make accessible/physically prepare those materials for which shelf-ready is not available, to provide scholarly access to unique or rarely-held resources in all subjects, formats, and languages. Identify strategies to keep up with locally-selected licensed e-resources. | All | existing staff; DCS | Measurement: Incoming cataloging requests: Backlog size grows no larger over the course of the year. | 2011-07-01 | Goal C: Make Specialized Collections Accessible
7 | Adopt strategies for improving cataloging efficiency, in order to expand capacity for metadata work across the department. | All | existing staff; Print Acq; Tech Processing Workflows TF | Measurement: In collaboration with Print Acquisitions, an examination will be done of activities performed in both units. | 2011-07-01 | Goal C: Make Specialized Collections Accessible
8 | Expand shelf-ready to include more than one vendor. | Train & Doc | existing staff; Print Acq; Tech Processing Workflows TF; LIT | Measurement: YBP will no longer be the only vendor that supplies this service. Additional vendords, e.g. Coutts will be set up. The possibility of using Aux Amateurs will be explored. | 2011-07-01 | Goal D: Enrich Services
9 | Expand copy cataloging on receipt for mainstream print monographs | Metadata TF; Train & Doc | existing staff; Print Acq; Tech Processing Workflows TF | Measurement: For the monographs with copy available at the time of receipt that can be used largely as-is, appropriate acquisitions staff are trained to receive & identify correct matching record and set UCLA's symbol in WorldCat. Efforts will be coordinated with shelf-ready opportunities. | 2010-09-30 | Goal D: Enrich Services
10 | Rush process approximately 3,000 titles to meet specific user needs. Reexamine workflow and tracking ability, now that a 3rd department, Preservation, has entered the picture | All | existing staff; Print Acq; Preservation | Measurement: Those patron-initiated requests for items already in the workflow are located within a day and given to a cataloger to work on. All rush titles, including those that were ordered rush, get out of the department within 24-48 hours. | 2011-07-01 | Goal C: Make Specialized Collections Accessible Goal D: Enrich Services
11 | Maintain the currency of records for ongoing publications | Auth/DBM; Continuing Resources; Dig Res Metadata; Metadata TF; Train & Doc | existing staff | Measurement: Based on the publishers' change of behavior in serials, monographic sets, and integrating resources, catalog records for those publications are updated in OCLC. | 2011-07-01 | Goal C: Make Specialized Collections Accessible
12 | Create & maintain consistency and links among headings across all Library discovery tools through use of authority records that will enhance the ability to find resources. | All | $17K/yr. for vendor services; LIT for extracting and loading Voyager records | Measurement:Authority work on digital library projects is as prominent as that for Voyager's cataloging records. Experimentation will be done to submit new names and subjects from digital metadata to the national file; subject term contributions to other vocabularies, e.g. AAT, TGM, will be attempted and reported on. Action is completed on the reports generated by authority vendor during the year. | 2011-07-01 | Goal C: Make Specialized Collections Accessible
13 | Problem solve and perform database maintenance (ongoing) Exs.: Follow up on OCLC reclamation project "unresolved records" Create and submit Local Holdings Records (LHRs) as needed to support WorldCat Local. | Train & Doc; Auth-DBM; Continuing Resources; Dig Res Metadata; Phys Proc | existing staff; LIT | Measurement: Incoming maintenance requests and problem reports are prioritized and dealt with in a reasonable turnaround time within existing resources. Additional batch automation strategies will be attempted, prior to working on unresolved records manually. | 2011-07-01 | Goal C: Make Specialized Collections Accessible
14 | Foster and support new uses of the work of our unit, through standards development, data element mapping, metadata provision and maintenance. Provide metadata consultations as requested | Train & Doc; Auth-DBM; Continuing Resources; Dig Res Metadata; Monocats | existing staff; DCS; DLP; LIT | Measurement: Assistance is given as needed, e.g. for those assigning preliminary metadata for the Web Archiving Service, etc. Metadata consultations with the campus community are made as warranted. As we become aware of the need, we offer to Library colleagues tip sheets, search strategies, and other tools that help users more easily find research materials. Insights on how to improve metadata content and practices are brought back to the unit and appropriate solutions pursued. | 2011-07-01 | Goal C: Make Specialized Collections Accessible
Cooperative Partnerships
15 | Provide support and expertise to the UC-OCLC Next Generation Melvyl Pilot project | All | existing staff | Measurement: UC goes into production. Obstacles to progress are diagnosed and overcome, jointly with OCLC staff. Understanding of the mechanics and rationale for the project is widespread. | 2011-07-01 | Goal D: Enrich Services
16 | Support implementation of recommendations related to "Single Cataloging Enterprise" from the BSTF Report, as part of a successful Next Generation Melvyl pilot. As appropriate, participate in development of systemwide workflows, policies, training programs. | All | existing staff | Measurement: The UC CONSER Funnel is evaluated and support given. Cataloging records are contributed to the UC Shared Print program. Language expertise is shared with other institutions in a way that benefits UCLA. | 2011-07-01 | Goal C: Make Specialized Collections Accessible
17 | Expand the range and depth of our abilities to contribute and maintain bibliographic & authority records at the network level. | Auth/DBM; Continuing Resources; Metadata TF; Monocats | existing staff | Measurement: A majority of Metadata TF will make contributions to OCLC's Expert Community. Contributions are made to new & existing NACO funnel projects. Contributions of original scripts to authority records are made at the national level. | 2011-07-01 | Goal C: Make Specialized Collections Accessible
18 | Contribute bibliographic and authority records to the Program for Cooperative Cataloging | Auth/DBM;Continuing Resources; Dig Res Metadata; Monocats | existing staff | Measurement: Contributions to CONSER, BIBCO, and NACO/SACO remain similar to existing levels. | 2011-07-01 | Goal C: Make Specialized Collections Accessible
19 | Participate in the first PCC cooperative project involving open access e-serials | Continuing Resources | existing staff | Measurement: UCLA's contributions of authenticated CONSER records will be seen in WorldCat for the Directory of Open Access Journals (DOAJ), which supports scholarly communication. Third-party service providers like Serials Solutions will have the records they need for this widely-requested package. | 2011-07-01 | Goal D: Enrich Services
20 | Contribute to the discussion and development of "communal LHRs" for storage of preservation data at the network level | Continuing Resources | existing staff; Preservation Ofcr | Measurement: Advice, solutions, etc. are provided to OCLC and other parties. Examples are developed from real preservation action data to support the proposal to move MARC 583 fields from serial bibliographic to holding records. | 2011-07-01 | Goal D: Enrich Services
21 | Assist in regional/national development of cataloging guidelines and their implementation, including RDA and the BIBCO Standard Record.. | Auth/DBM; Continuing Resources; Monocats; Dig Res Metadata | existing staff | Measurement: Resource Description and Access (RDA) is tested via Music Lib Assn/OLAC involvement and evaluative comments suggested; contributions are made to RLG Partners Metadata Managers Group. Contribute to the assessment of the new BIBCO Standard Record. | 2011-07-01 | Creation of metadata, adherence to descriptive standards (p.9): New standards … for description … will be implemented to maximize access to research collections (p.10)
22 | Support the utility of our work beyond the catalog, through standards development, data element mapping, metadata provision and maintenance. | All | existing staff | Measurement: Metadata consultations with the campus community are made as warranted. As we become aware of the need, we offer to Library colleagues tip sheets, search strategies, and other tools that help users more easily find research materials. Insights on how to improve metadata content and practices are brought back to the unit and appropriate solutions pursued. | 2011-07-01 | Goal D: Enrich Services
23 | Load record sets received from outside sources | Dig Res Metadata; Continuing Resources; Train & Doc; LIT | existing staff | Measurement: Records from the Shared Cataloging Program, Marcive's Documents Without Shelves, etc. are loaded quickly and problems are resolved within a month of receipt. | 2011-07-01 | Goal C: Make Specialized Collections Accessible
Infrastructure
24 | Normalize metadata workflow | Dig Res Metadata; Metadata TF | existing staff; DLP | Measurement: Digital projects will regularly be taking place concurrently and upcoming project priorities will be known at least a month in advance. Data input can originate either in DLCS or in OCLC Connexion. Completed projects published in DLCS will be OAI harvested by OCLC for inclusion in WorldCat. | 2011-07-01 | Goal D: Enrich Services
25 | Normalize workflow for e-resources | All | existing staff; DCS | Measurement: Notification of new and changed resources will occur promptly after access is licensed. Resources will be systematically set up in the ERM prior to notification. | 2011-07-01 | Goal D: Enrich Services
26 | Assess, evaluate and improve department operations | All | existing staff; most other units | Measurement:The boundary lines between Cat-Met and adjacent units are reconsidered. With shift of duties toward Preservation, workflows are reviewed. An automated method of counting withdrawal stats from Voyager activity will be experimented with. | 2011-07-01 | Goal C: Make Specialized Collections Accessible
27 | Experiment with digital library project input directly into OCLC Connexion and with the results of programming in DLCS to streamline authority record input. | All | existing staff; LIT; DLP | Measurement: Familiarity with strengths and weaknesses of CONTENTdm and DLCS will be developed. | 2011-07-01 | Goal D: Enrich Services
Harnessing Automation
28 | Assist in implementation of Serials Solutions as an E-Resource Management System tool | Cont Res Cat; Dig Res Metadata | existing staff; DCS; LIT | Measurement: Overlap among WCL, Voyager, ERDb, SFX, and the new ERM is determined and a rational dataflow is designed. Center expertise contributed as warranted. | 2011-07-01 | Goal D: Enrich Services
29 | Develop new means of scripting creation of metadata and/or acquiring metadata from outside sources, to enhance the catalog | Dig Res Metadata; Train & Doc; Continuing Resources | TACs; existing staff; LIT | Measurements: Data transformation goes both ways--toward MARC and toward non-MARC. | 2011-07-01 | Goal C: Make Specialized Collections Accessible
30 | Define and develop automated measures for quantifying our digital library work. | All | DLP; existing staff | Measurement: A meaningful analysis of Center metadata creation efforts is possible. | 2011-07-01 | Goal D: Enrich Services
Succession Management and Planning
31 | Creatively cover by reorganization and other means the needs created by vacancies in the unit. | All | LHR; existing staff | Measurement: A combination of reassignments, collaborations, cross-training, and outside recruitments is used to cover a maximum of the unit's emerging needs. | 2011-07-01 | Goal C: Make Specialized Collections Accessible
32 | Provide internship opportunities for multiple library school students | Monocats; Continuing Resources | existing staff | Measurement: The library school internship fair is attended, prospective interns are assessed, and at least two internships are conducted in the Center. | 2011-07-01 | Goal C: Make Specialized Collections Accessible
Learning Organization
33 | Work creatively to assure continued access to training and development among our staff, in the current budget climate. Encourage all members of the unit to create learning & development goals that may include training & development. | All | existing staff | Measurement: Tools such as Elluminate are utilized to lower the cost of giving & receiving learning/development. Travel funding needs for a maximum number of staff are identified at the beginning of the year, permitting better planning. At least a dozen meetings of the Catalogers Group are organized. | 2011-07-01 | Goal D: Enrich Services
34 | Develop the unit's metadata expertise, contributions, and reputation. | Sect Hds | $500; existing staff | Measurement: The 21st Century course "Metadata & Digital Library Development" will be brought to UCLA. The unit's reputation will rival what has historically been achieved with MARC-based AACR2 cataloging. | 2011-07-10 | Goal C: Make Specialized Collections Accessible
35 | Develop and deliver training in RDA. | Sect Hds; Monocats | existing staff; ACCM | Strong familiarity with RDA is developed in conjunction with UC's CAMCIG. Training is tailored as necessary for cataloging-on-receipt staff. | 2010-10-10 | Goal D: Enrich Services
36 | Take part directly in Library's provision of public service | All | existing staff | Measurement: Approx. half a dozen staff are involved for 1-2 hours/week. Insights into how users are using or are assisted by metadata are shared within the Center. | 2011-07-01 | Goal D: Enrich Services
37 | Mainstream knowledge and use of Elluminate software in the unit | All | existing staff | Measurement: The necessary training is identified and conducted. | 2011-07-01 | Goal D: Enrich Services
Collection Consolidation
38 | Support the Chemistry Library closure | All | existing staff | Material is transferred, reclassified, relabeled, or withdrawn, as needed. | 2011-07-01 | Goal C: Make Specialized Collections Accessible