## Sheet1
| Work Task | Sections Responsible | Resources Required | Goals/Measurement | Date Due | Relevant Strategic Plan Element
Organizing and Providing Access to Material
1 | Expand metadata activity among Center staff. E.g. begin providing geotagging; catalog maps to be digitized; begin describing motion picture stills; complete Walter Gordon, Bonnie Cashin, and other projects. | All | existing staff; ability to significantly expand shelf ready processing and to depend on cat-on-receipt | Measurement: Digital projects regularly take place concurrently. It will be common for staff to spend at least one day a week on metadata activity. Stats capability in Islandora will be explored for tracking digital project activity; baselines will be established. | 2012-07-01 | Goal C: Make Specialized Collections Accessible
2 | Explore and identify metadata roles in connection with new Research Commons at YRL. | Catalogers Group | existing staff; CRIS | Measurement: Discussions will be held with CRIS to exchange ideas. Awareness of the types of projects taking place will be developed. Regular communication with the Librarian for Digital Research & Scholarship takes place. Advice on how to draw on materials in Library's collections will be offered as warranted. Completed Research Commons projects will be described as warranted. | 2012-07-01 | Goal D: Enrich Services Goal H: Create Research Agenda for the Library
3 | With Biomed Library staff, respond to researcher-expressed needs for information about metadata and how it fits into their research and data work. | Catalogers Group | existing staff; Biomed Lib | Measurement: Recent MLA meeting presentations about "translational research" are reviewed & discussed by Library staff. Additional conversations and information sharing sessions are held with School of Medicine staff as warranted. | 2012-07-01 | Goal D: Enrich Services Goal H: Create Research Agenda for the Library
4 | Launch new Discovery Team and expand involvement in bibliographic control of hidden collections material | Discovery Team | Project staff primarily; other existing staff as needed; LSC; Arcadia funding | Measurement: The greatest needs among the Library's hidden collections are prioritized & worked on. At least 2 projects are completed by the Team. Multiple formats including serials are tackled. The Team & its work are effectively integrated into the Center. Center staff also gain experience with forms of bibliographic control used in Library Special Collections. | 2012-07-01 | Goal C: Make Specialized Collections Accessible
5 | Expand Arcadia-funded Nitrates Project beyond L.A. Daily News images | Dig Res Metadata | existing staff & Arcadia-funded temp Lib Assts + students | Measurement: The cumulative total of images described in the project increases from 2K to 10K. | 2012-07-01 | Goal C: Make Specialized Collections Accessible
6 | Prepare priority batches of Library materials for Google digitization by completing non-roman recon. Support Internet Archive digitization workflow. | Metadata TF; Monocats | existing staff & students; possibly some limited appt funding [being assessed] | Measurement: Throughout the year selected priority classification ranges are completed and the material is folded into shipments to Google or the Internet Archive. | 2012-07-01 | Goal C: Make Specialized Collections Accessible
7 | Eliminate backlogs and consolidate leftovers. Expand implemention of new strategies, including experimenting with "floating" limited appointments or students with specific language skills who could meet needs in various Library areas | Eliminating Backlogs & Improving Bibliographic Access Group | existing staff | Measurement: Some backlogs will be cited as being eliminated/reduced. Minimal level cataloging will be caught up, except where language skills are lacking. Maps are cataloged in support of digitization. | 2012-07-01 | Goal C: Make Specialized Collections Accessible
8 | Increase access to Non-Roman/Specialized Material/Hidden Collections. Increase familiarity with the types of bibliographic control used with special collections materials. | All; Print Acq; assistance from CRIS | existing staff | Measurement: Provisional access to newly-received non-roman material is brought about through collaboration with Print Acq on a pilot for vernacular-only data input for at least one language. Collection-level records are employed for appropriate materials, for which we lack the necessary language expertise. Armenian Minasian commerce letters are organized for digitization and described. | 2012-07-01 | Goal C: Make Specialized Collections Accessible
9 | Catalog and make accessible/physically prepare those materials for which shelf-ready is not available, to provide scholarly access to unique or rarely-held resources in all subjects, formats, and languages. Identify strategies to keep up with locally-selected licensed e-resources. | All | existing staff; SCL | Measurement: Incoming cataloging requests: Backlog size grows no larger over the course of the year. | 2012-07-01 | Goal C: Make Specialized Collections Accessible
10 | Adopt strategies for improving cataloging efficiency, in order to expand capacity for metadata work across the department. | All | existing staff; Print Acq; Tech Processing Workflows TF | Measurement: In collaboration with Print Acquisitions, an examination will be done of activities performed in both units. | 2012-07-01 | Goal C: Make Specialized Collections Accessible
11 | Expand shelf-ready to include more than one vendor. | 'Get It' team | existing staff; Print Acq; Tech Processing Workflows TF; LIT | Measurement: YBP will no longer be the only vendor that supplies this service. Additional vendords, e.g. Coutts will be set up. The possibility of using Aux Amateurs will be explored. | 2012-07-01 | Goal D: Enrich Services
12 | Expand copy cataloging on receipt for mainstream print monographs | Metadata TF; 'Get It' team | existing staff; Print Acq; 'Get It' team | Measurement: For the monographs with copy available at the time of receipt that can be used largely as-is, appropriate acquisitions staff are trained to receive & identify correct matching record and set UCLA's symbol in WorldCat. Efforts will be coordinated with shelf-ready opportunities. | 2012-07-01 | Goal D: Enrich Services
13 | Take over ERM maintenance work (see also #28) | Continuing Resources; Dig Res Metadata | existing staff; SCL | Measurement: Work will be getting done in a systematic manner, with data aligned across Voyager, SFX, Serials Solutions ERM. | 2012-07-01 | Goal C: Make Specialized Collections Accessible Goal D: Enrich Services
14 | Rush process approximately 3,000 titles to meet specific user needs. | All | existing staff; Print Acq; Preservation | Measurement: Those patron-initiated requests for items already in the workflow are located within a day and given to a cataloger to work on. All rush titles, including those that were ordered rush, get out of the department within 24-48 hours. Key players have back ups. | 2012-07-01 | Goal C: Make Specialized Collections Accessible Goal D: Enrich Services
15 | Maintain the currency of records for ongoing publications | Auth/DBM; Continuing Resources; Dig Res Metadata; Metadata TF; Principal Cataloger | existing staff | Measurement: Based on the publishers' change of behavior in serials, monographic sets, and integrating resources, catalog records for those publications are updated in OCLC. | 2012-07-01 | Goal C: Make Specialized Collections Accessible
16 | Create & maintain consistency and links among headings across all Library discovery tools through use of authority records that will enhance the ability to find resources. | All | $17K/yr. for vendor services; LIT for extracting and loading Voyager records | Measurement: Authority work on digital library projects is as prominent as that for Voyager's cataloging records. Experimentation will be done to submit new names and subjects from digital metadata to the national file; subject term contributions to other vocabularies, e.g. AAT, TGM, will be attempted and reported on. Action is completed on the reports generated by authority vendor during the year. Usage of Gary Strawn's Catalogers' Toolkit is maintained and its new capabilities are explored. | 2012-07-01 | Goal C: Make Specialized Collections Accessible
17 | Problem solve and perform database maintenance (ongoing) Exs.: Follow up on OCLC reclamation project "unresolved records" Create and submit Local Holdings Records (LHRs) as needed to support WorldCat Local. | Auth-DBM; Continuing Resources; Dig Res Metadata; Phys Proc; Principal Cataloger | existing staff; LIT | Measurement: Incoming maintenance requests and problem reports are prioritized and dealt with in a reasonable turnaround time within existing resources. Additional batch automation strategies will be attempted, prior to working on unresolved records manually. | 2012-07-01 | Goal C: Make Specialized Collections Accessible
18 | Foster and support new uses of the work of our unit, through standards development, data element mapping, metadata provision and maintenance. Provide metadata consultations as requested | All | existing staff; SCL; DLP; LIT | Measurement: Assistance is given as needed, e.g. new RDA elements in authority records in support of campus TEI mark up work, geotagging. Metadata consultations with the campus community are made as warranted. As we become aware of the need, we offer to Library colleagues tip sheets, search strategies, and other tools that help users more easily find research materials. Insights on how to improve metadata content and practices are brought back to the unit and appropriate solutions pursued. | 2012-07-01 | Goal C: Make Specialized Collections Accessible
Cooperative Partnerships
19 | Provide support and expertise to WorldCat Local (Melvyl) | All | existing staff; CDL | Measurement: Work to support new functionality gets done. Obstacles to progress are diagnosed and overcome, jointly with OCLC staff. Understanding of the mechanics and rationale for the project is widespread. | 2012-07-01 | Goal D: Enrich Services
20 | Support the "Single Cataloging Enterprise" concept from the BSTF Report. As appropriate, participate in development of systemwide workflows, policies, training programs. | All | existing staff | Measurement: The UC CONSER Funnel is evaluated and support given. Cataloging records are contributed to the UC Shared Print program. Language expertise is shared with other institutions in a way that benefits UCLA. Staff participate in the NGTS implementation effort. | 2012-07-01 | Goal C: Make Specialized Collections Accessible Goal D: Enrich Services
21 | Contribute and maintain bibliographic records at the network level. | Auth/DBM; Continuing Resources; Metadata TF; Monocats | existing staff | Measurement: A majority of Metadata TF will make contributions to OCLC's Expert Community. Non-roman script is routinely added to bibliographic records. | 2012-07-01 | Goal C: Make Specialized Collections Accessible
22 | Contribute bibliographic and authority records to the Program for Cooperative Cataloging | Auth/DBM;Continuing Resources; Dig Res Metadata; Monocats | existing staff | Measurement: Contributions are made to CONSER, BIBCO, and NACO/SACO. Contributions are made to new & existing NACO funnel projects. Contributions of original scripts to authority records are made at the national level. Leadership is provided for PCC Arabic NACO Funnel project. | 2012-07-01 | Goal C: Make Specialized Collections Accessible
22 | Contribute to the WEST project pilot and the development of "communal LHRs" for storage of preservation data at the network level | Continuing Resources | existing staff; Preservation Ofcr; LIT; SRLF | Measurement: Advice, solutions, etc. are provided to OCLC and other parties. Examples are developed from real preservation action data to support the proposal to move MARC 583 fields from serial bibliographic to holding records. | 2012-07-01 | Goal D: Enrich Services
23 | Assist in regional/national development of cataloging guidelines and their implementation, including RDA and the BIBCO Standard Record. | Auth/DBM; Continuing Resources; Monocats; Dig Res Metadata | existing staff | Measurement: Contributions are made to policy discussions at the national level re: Resource Description and Access (RDA); contributions are made to RLG Partners Metadata Managers Group. | 2012-07-01 | Goal D: Enrich Services
24 | Support the utility of our work beyond the catalog, through standards development, data element mapping, metadata provision and maintenance. | All | existing staff | Measurement: Metadata consultations with the campus community are made as warranted. As we become aware of the need, we offer to Library colleagues tip sheets, search strategies, and other tools that help users more easily find research materials. Insights on how to improve metadata content and practices are brought back to the unit and appropriate solutions pursued. | 2012-07-01 | Goal D: Enrich Services
25 | Load record sets received from outside sources | Dig Res Metadata; Continuing Resources; LIT | existing staff | Measurement: Records from the Shared Cataloging Program, Marcive's Documents Without Shelves, various e-book packages, etc. are loaded quickly and problems are resolved within a month of receipt. | 2012-07-01 | Goal C: Make Specialized Collections Accessible
Infrastructure
26 | Increase metadata workflow | Dig Res Metadata; Metadata TF | existing staff; DLP | Measurement: Digital projects regularly take place concurrently and upcoming project priorities will be known at least a month in advance. Metadata can originate either in the local input tool or in OCLC Connexion. Completed projects will be harvested by OCLC and others for inclusion in WorldCat and elsewhere. | 2012-07-01 | Goal D: Enrich Services
27 | Integrate RDA into our work and help develop related policies that are needed. (see also #38) | All | existing staff | Measurement: Strong familiarity with the new cataloging code is developed. Non-energy-intensive means of implementing the new rules are used, while a maximum of the benefits are gained. Contributions are made to policy discussions at the national level. Changes needed in Voyager, workflows or local policies are addressed. | 2012-01-01 | Goal D: Enrich Services
28 | Refine workflow for e-resources (see also #13) | All | existing staff; DCS | Measurement: Notification of new and changed resources will occur promptly after access is licensed. Resources will be systematically set up in the ERM prior to notification. Outreach to selectors is done; a cataloging request mechanism is developed. | 2012-07-01 | Goal D: Enrich Services
29 | Expand opportunities for improving workflow across Kinross departments. | Tech Processing Workflows TF; 'Get It' team; section heads | existing staff; Print Acq | Measurement: In support of continuous improvement efforts, staff reflect on the work performed on a daily basis across the technical services units in order to make concrete suggestions about how it could be done differently. | 2012-07-01 | Goal D: Enrich Services
30 | Expand knowledge of needs and issues faced in other Library units | All | existing staff; most other units | Measurement: Systematic liaison relationships with all our constituents. What is learned is acted on. | 2012-07-01 | Goal D: Enrich Services
31 | Help migrate to and implement Islandora, for digital library project work. Explore possible reliance on linked data approach and/or OCLC's Terminology Service for authority work. | All | existing staff; DLP; LIT | Measurement: Advice on migration of DLCS metadata provided as requested. Participation in testing of data entry, feedback, suggesting of improvements occurs as warranted. | 2012-07-01 | Goal D: Enrich Services
Harnessing Automation
32 | Assist in ongoing development of Serials Solutions as an E-Resource Management System tool | Cont Res Cat; Dig Res Metadata | existing staff; DCS; LIT | Measurement: Overlap among WCL, Voyager, SFX, and the new ERM is determined and a rational dataflow is designed. Center expertise contributed as warranted. | 2012-07-01 | Goal D: Enrich Services
33 | Develop new means of scripting creation of metadata and/or acquiring metadata from outside sources, to enhance the catalog | Dig Res Metadata; Continuing Resources | TACs; existing staff; LIT | Measurements: Data transformation goes both ways--toward MARC and toward non-MARC. Use of MARCedit and other tools that can manipulate batches of records is explored. Cat-Met articulates specific needs in the area of batch actions on metadata, data manipulation, macro development, etc. and explores with LIT possibilities of meeting the needs with exisitng LIT staff resources. | 2012-07-01 | Goal C: Make Specialized Collections Accessible
Succession Management and Planning
34 | Creatively cover by reorganization and other means the needs created by vacancies in the unit. | All | LHR; existing staff | Measurement: A combination of reassignments, collaborations, cross-training, and outside recruitments is used to cover a maximum of the unit's emerging needs. | 2012-07-01 | Goal C: Make Specialized Collections Accessible
35 | Provide internship opportunities for multiple library school students | Monocats; Continuing Resources; Dig Res Metadata | existing staff | Measurement: The library school internship fair is attended, prospective interns are assessed, and at least two internships are conducted in the Center. | 2012-07-01 | Goal G: Build/Nurture a Sustainable & Responsible Organization
Learning Organization
36 | Work creatively to assure continued access to training and development among our staff, in the current budget climate. Encourage all members of the unit to create learning & development goals that may include training & development. | All | existing staff | Measurement: Tools such as Elluminate are utilized to lower the cost of giving & receiving learning/development. Travel funding needs for a maximum number of staff are identified at the beginning of the year, permitting better planning. At least a dozen meetings of the Catalogers Group are organized. | 2012-07-01 | Goal D: Enrich Services
37 | Develop the unit's metadata expertise, contributions, and reputation. | Sect Hds | existing staff | Measurement: Training opportunities are identified and taken advantage of. The unit's reputation will rival what has historically been achieved with MARC-based AACR2 cataloging. | 2012-07-10 | Goal C: Make Specialized Collections Accessible
38 | Develop and deliver training in RDA. | Sect Hds; Monocats | existing staff; ACCM | Strong familiarity with RDA is developed in conjunction with UC's CAMCIG. Training is tailored as necessary for cataloging-on-receipt staff and public service staff. | 2012-01-01 | Goal D: Enrich Services
39 | Take part directly in Library's provision of public service | All | existing staff | Measurement: Approx. half a dozen staff are involved for 1-2 hours/week. Insights into how users are using or are assisted by metadata are shared within the Center. | 2012-07-01 | Goal D: Enrich Services
Collection Consolidation
40 | Support the Chemistry Library closure | All | existing staff | Material is transferred, reclassified, relabeled, or withdrawn, as needed. | 2012-01-01 | Goal C: Make Specialized Collections Accessible